Currency Converter — Project Plan

Mid-Level Flutter Engineer Assessment  ·  Internal Planning Document  ·  Budget 4–6 Hours

| Task | Build order & time-boxed plan for the Currency Converter take-home |
| --- | --- |
| Priority key | Must-Have = required by brief · Should-Have = quality bar · Optional = time-permitting |

O V E R V I E W

# Scope Summary

Flutter app with two screens (Converter, History) sharing one feature module, built on Clean Architecture with flutter_bloc, live rates from frankfurter.app, and local persistence via Hive. Full standard is documented in the project's CLAUDE.md.

P L A N

# Task Breakdown, In Build Order

Ordered to match dependency order (domain before data before presentation) and to keep every Must-Have feature working before any Should/Optional work begins.

| Phase | Task | Priority | Est. |
| --- | --- | --- | --- |
| 1. Setup | Scaffold folders, pubspec deps, DI/theme/Dio boilerplate | Must | 20m |
|  | Git init, .gitignore, first commit, public repo created | Must | 10m |
| 2. Domain Layer | Entities: ExchangeRate, ConversionRecord | Must | 15m |
|  | Repository contract (abstract, Either) | Must | 10m |
|  | Use cases: GetExchangeRate, SaveConversion, GetHistory | Must | 20m |
|  | Use case: DeleteHistoryEntry | Optional | 10m |
| 3. Data Layer | Remote data source: frankfurter.app client + models | Must | 30m |
|  | Local data source: Hive box for conversion history | Must | 25m |
|  | Repository impl (BaseRepository pattern, exception→Failure mapping) | Must | 25m |
|  | compute()-based JSON parsing for list responses | Should | 10m |
|  | Last-cached-rate fallback for offline use | Optional | 20m |
| 4. Presentation — Converter | ConverterCubit: Loading/Error/Success sealed states | Must | 25m |
|  | Form UI + validation (empty/zero/negative/non-numeric) | Must | 30m |
|  | Result display via intl NumberFormat.currency | Must | 10m |
|  | Same-currency-selected handling | Should | 10m |
|  | Duplicate-submit guard (droppable() transformer) | Should | 10m |
| 5. Presentation — History | HistoryCubit reading persisted conversions | Must | 20m |
|  | Reusable list item widget + empty/loading/error states | Must | 20m |
|  | Delete individual history entry (swipe or button) | Optional | 15m |
| 6. Design System | Centralised theme: color palette, type scale, spacing tokens | Must | 20m |
|  | Reusable widgets: AppTextField, AppButton, AppSnackbar, list tile | Must | 20m |
|  | Responsive breakpoint (constrain form width on tablet) | Must | 15m |
|  | Dark mode via theme tokens | Optional | 20m |
| 7. Testing | Bloc tests (state sequences, both screens) | Should | 30m |
|  | Use case tests (Left/Right branches) | Should | 20m |
|  | Repository failure-mapping tests | Optional | 15m |
|  | Widget test for Loading/Error/Success | Optional | 15m |
|  | Golden test, primary screen | Optional | 10m |
| 8. Wrap-up | flutter analyze + dart format clean | Must | 10m |
|  | README: setup, architecture, design system, AI usage note | Must | 25m |
|  | Fresh clone + flutter run verification | Must | 10m |
|  | ASSUMPTIONS.md / DECISIONS.md | Optional | 10m |

Time budget: Must-Have items alone total roughly 4h10m — matches the stated 4–6h window with room for a handful of Should-Have items. Optional items are only started once every Must-Have box above is checked.

J U D G M E N T

# Risks & Assumptions

| Risk / Ambiguity | Resolution |
| --- | --- |
| Exact validation rule for invalid amounts not specified | Reject empty, zero, negative, and non-numeric input client-side before any API call. |
| Behaviour when base = target currency not specified | Show a 1:1 result rather than blocking submission; document as an assumption. |
| frankfurter.app rate limits / downtime during review | Add a cached-last-rate fallback (optional scope) so a demo doesn't hard-fail on network issues. |
| Tablet layout not detailed in brief | Single responsive breakpoint constraining form width; no separate tablet-only screens. |

Reference: architecture standard in CLAUDE.md  ·  requirements in EFG_Flutter_Assessment.pdf